## CD3
Initative | Estimated effort (in weeks) | One-time value ($) | CD3 - Cost of Delay / Duration
A | 4 | 1500 | 0.375
B | 2 | 2000 | 1
C | 10 | 8500 | 0.85
D | 8 | 6000 | 0.75
Scenario 1: No priority
Do everything at once and complete them all at the same time
If you work on all of the features at once, it will be 24 weeks until you see any value. Therefore, you eat the value of each feature for the full 24 weeks. That means you lose the entire $18,000 each week for 24 weeks, for a total of $432,000 Cost of Delay.
Initative | Estimated effort (in weeks) | One-time value ($) | CD3 - Cost of Delay / Duration
A | 4 | 1500 | 0.375
B | 2 | 2000 | 1
C | 10 | 8500 | 0.85
D | 8 | 6000 | 0.75
Total | 24 | 18000
Total time to value | 24
Cost of Delay | 432000
Scenario 2: Duration priority
Do the shortest duration first, then the next and so on.
You would delay realising the value of each feature until it and any features that come before it are delivered. That works out to a total Cost of Delay of $301,000, calculated as follows
Initative | Estimated effort (in weeks) | One-time value ($) | Cost
B | 2 | 2000 | 4000
A | 4 | 1500 | 9000
D | 8 | 6000 | 84000
C | 10 | 8500 | 204000
Total time to value | 24
Cost of Delay | 301000
Scenario 3: Value priority
Do the highest value first, then the next and so on.
You would delay realising the value of each feature until it and any features that come before it are delivered. That works out to a total Cost of Delay of $259,500, calculated as follows:
Initative | Estimated effort (in weeks) | One-time value ($) | Cost
C | 10 | 8500 | 85000
D | 8 | 6000 | 108000
B | 2 | 2000 | 40000
A | 4 | 1500 | 36000
Total time to value | 24
Cost of Delay | 269000
Scenario 4: CD3 Option
Do the highest CD3 value first, then the next and so on.
You would delay realising the value of each feature until it and any features that come before it are delivered. That works out to a total Cost of Delay of $259,500, calculated as follows:
Initative | Estimated effort (in weeks) | One-time value ($) | CD3 | Cost
B | 2 | 2000 | 1 | 4000
C | 10 | 8500 | 0.85 | 102000
D | 8 | 6000 | 0.75 | 120000
A | 4 | 1500 | 0.375 | 36000
Total time to value | 24
Cost of Delay | 262000
Compare Options
Comparing your options side by side, you have an easy choice when it comes to Cost of Delay, with the CD3 prioritisation option costing the least amount of money.
Prioritisation Option | Cost of Delay
Scenario 4: CD3 Option | 262000
Scenario 3: Value priority | 269000
Scenario 2: Duration priority | 301000
Scenario 1: No priority | 432000

## Advanced NVP
Assumptions | Data
Analysis horizon | 52 | How far out to count recurring benefits.
Annual decay rate | 10% | Used to PV benefits/costs from delay.
Weekly decay rate | 0.1835% | Derived: (1+annual)^(1/52)-1.
Initative | Estimated effort (in weeks) | Probability of success (%) | Recurring value ($) | Recurring penalty ($) | One-time value ($) | Cost of delay per week | One-time delivery benefit ($) | CD3 Value | Delay + (4 weeks) | Delay + (8 weeks) | Delay + (12 weeks)
A | 4 | 80% | 1000 | 500 | 10000 | 1200 | 7941.5621 | 0.3 | 12661.6167 | 17347.1925 | 21998.5415
B | 2 | 90% | 5000 |  | 2000 | 4500 | 1793.4137 | 2.25 | 19698.0596 | 37471.9167 | 55115.9404
C | 10 | 50% | 4500 |  | 25000 | 2250 | 12272.9759 | 0.225 | 21142.1981 | 29946.633 | 38686.7538
D | 8 | 70% |  | 10000 |  | 7000 | 0 | 0.875 | 27872.0499 | 55540.5016 | 83006.8424
How to read this model: The true cost of delay
WHAT THIS TOOL DOES This calculator shows the real economic impact of waiting to start an initiative. It answers one simple question: If we delay this work by 4, 8 or 12 weeks, what does that cost us in today’s
dollars?
WHAT GOES INTO THE MODEL Each initiative is assessed using four inputs.
1. Weekly impact
The value we gain or pain we avoid each week once thinitiative is delivered.
2. Probability of success We use expected value, not best-case scenarios.
3. One-off benefit Any single, material gain that only happens at delivery. Examples include a contract renewal, licence saving or avoided fine.
4. Time value of money Value received later is worth slightly less than value received today, so future benefits are adjusted back to today’s dollars.
WHAT THE KEY NUMBERS MEAN
Cost of delay per week This is the weekly value we lose by waiting, adjusted for risk. It shows the ongoing pain of delay.
One-time delivery benefit (NPV) This is the one-off value of delivery, shown in today’s dollars. It is not spread across weeks. It happens once, at go-live.
Delay plus 4, 8 and 12 weeks These columns show the total economic impact of waiting that long, including: - the weekly value lost while we wait - the reduced value of the one-off benefit because it arrives later
HOW TO READ A ROW Take any initiative and read across.
Cost of delay per week tells you how expensive waiting is, week by week. Delay plus 4 weeks shows the impact of waiting one month. Delay plus 8 weeks shows the impact of waiting two months. Delay plus 12 weeks shows the impact of waiting three months.
The numbers grow because delay compounds.
HOW TO USE THIS IN DECISIONS Use this model to: -Compare which delays are most expensive, not just which work feels urgent. - Sequence initiatives by economic impact, not opinion. - Make trade-offs visible.
For example, if we choose to delay this by 8 weeks, we are choosing to give up about X dollars.
WHAT THIS IS NOT This is not a perfect financial forecast. It is a
decision tool that makes the cost of waiting visible so teams and
leaders can make better trade-offs.
ONE SENTENCE SUMMARY
This model turns delay into a dollar figure so prioritisation becomes an economic decision, not a debate about urgency.